## Open
Snape Village Maintenance - Topics & Actions
Date | Maintenance Topic | Owner | Actions | Target Date | Complete | Cost
2020-08-01 | Road signage near Silver Howe | S. Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
| - Carthorpe Sign bent / broken |  | - Response received | 2020-09-01 | 2020-09-01 | 0
| - Others old / dirty |  | - Sign to be repaired / replaced | 2020-11-01 |  | 0
|  |  | - Tree to be cut back to allow visibility | 2020-11-01 | 2020-10-01 | Complete
2020-08-01 | Benches (5) on Green and in Avenue in need of maintenance | S.Pringle | Identify volunteers to do work | 2020-10-01 | 2020-10-01 | £100 est
|  |  | - Russ / Sarah Simms renovating the one at the top of the Avenue | 2020-12-01 | In progress | 0
|  |  | - One at bottom of Avenue (near bend) to be allocated | 2021-06-01 |  | 0
2020-08-01 | Grass verges worn between Pennybeck & the bungalows | S.Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Highways not prepared to fund the work | 2020-09-01 | 2020-09-01 | 0
|  |  | - Costs received. PC to consider funding Spring / Summer 21 | 2021-07-01 | In progress | £4000 est
2020-08-01 | Pumps(2) on village green need restoring / repainting | S.Pringle | Identify volunteers to do work | 2020-10-01 | Complete | £73 est
2020-08-01 | & black metal bench on traingular green to repaint |  | - John Knopp, David Milner & Pringles to do work | 2020-12-01 | 2021-05-01 | 10
2020-08-01 | Mosaic Bridge & Road Bridge need painting | S.Pringle | Identify volunteers to do work | 2020-01-01 |  | £25 est
2020-08-01 | Road bridge near monument - upright & bar loose | J.Duck | John Duck / Richard Poole to undertake work | 2020-12-01 |  | £50 est
2020-08-01 | Grass verge near corner of alotments need attention | S.Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Highways agree to investigate further | 2020-11-01 |  | 0
2020-10-01 | Playing Fields - Rabbit holes need filling | C. Hodges | Top soil to be obtained from John Duck and work done | 2021-03-01 |  | 0
2020-11-01 | Playing Fields - Wooden picnic table to treat / paint | C. Hodges | Previous attempt unsuccessful | 2021-04-01 |  | £20 est
2021-05-01 | Playing Fields - Spinner on multi-play not rotating freely | R.Poole | Speak to Streetscape and ask for an opinion | 2021-05-01 |  | 0

## Closed
Snape Village Maintenance - Topics & Actions - COMPLETED
Date | Maintenance Issue | Owner | Actions | Target Date | Complete
2020-08-01 | 3 Neville Row - Garden & frontage overgrown | S.Lowe | Write to house owner | 2020-10-01 | 2020-10-01 | 0
|  |  | - Response received | 2020-10-01 | 2020-10-01
|  |  | - Owner will attend to internal bushes - confirmed done | 2020-11-01 | 2020-10-01
|  |  | - Owner has requested PC to change verge to hard stranding | Rejected | 2020-10-01
2020-08-01 | BT's intention to erect new pole near Cedar Garth to investigate | S.Lowe | Written to BT | 2020-09-01 | 2020-09-01 | 0
|  |  | - Await reply from BT | 2020-11-01 | 2020-11-01
|  |  | - Probably now superceeded by underground cabling | 2020-11-01 | 2020-11-01
2020-09-01 | Pavement outside Prices Paving Yard needs repair | S.Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Highways have agreed to repair & have done so | 2020-10-01 | 2020-10-01
2020-10-01 | Playing Fields - Post on multi-play rusting | C. Hodges | Post to be sanded down & painted | 2020-10-01 | 2020-10-01 | 0
2020-10-01 | Playing Fields - Underside of springer rusting | C. Hodges | Area needs rubbing down & painting | 2020-10-01 | 2020-10-01 | 0
2020-09-01 | Signage at top of Avenue / Well to Bedale Raod need repair | S.Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Highways to complete the work | 2020-10-01 | Otc 20
2020-08-01 | Institute bridge foundations need attention / resetting | J.Duck | Identify local contractor to undertake the work | 2020-10-01 | 2020-10-01 | £250 est
|  |  | - Agree contractor & cost | 2020-10-01 | 2020-10-01
|  |  | - Complete the work | 2020-11-01 | 2020-12-01
2020-08-01 | Mosaic bridge base needs re-pointing | J.Duck | Identify local contractor to undertake the work | 2020-10-01 | 2020-10-01 | £100 est
|  |  | - Agree contractor & cost | 2020-10-01 | 2020-10-01
|  |  | - Complete the work | 2020-11-01 | 2020-12-01
2020-09-01 | White Lines at junction of Meadow Lane / Avenue need repainting | S.Lowe | To be referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Order has been raised to refresh the lines | 2021-04-01 | 2020-12-01
2020-08-01 | White lines at junction of Meadow Lane / Ings Lane needs repainting | S.Lowe | Referred to Highways | 2020-09-01 | 2020-09-01 | 0
|  |  | - Response received | 2020-09-01 | 2020-09-01
|  |  | - Order has been raised to refresh the lines | 2021-04-01 | 2020-12-01
2020-08-01 | Benches (5) on Green and in Avenue in need of maintenance | S.Pringle | Identify volunteers to do work | 2020-10-01 | 2020-10-01 | £100 est
|  |  | - Colin Hodges will attend the one near the memorial | 2020-11-01 | 2020-11-01 | 0
|  |  | - Colin Hodges will attend the one near the mosaic bridge | 2020-12-01 | 2020-12-01 | 0
|  |  | - John Chesher will attend the one near the Institute | 2020-11-01 | Complete | 10
2020-08-01 | Black metal bench on traingular green to repaint |  | - John Knopp, David Milner & Pringles to do work | 2020-12-01 | 2021-05-01 | 10
2020-12-01 | Signage required at vllage entrance from Carthorpe | S.Lowe | Signage required to warn cyclists of dangerous bend | 2021-01-01 | Rejected | 0
|  |  | - Request to be sent to Highways with details of recent accident | 2021-01-01 | Rejected | 0
2020-08-01 | Beck clearing & maintenance | S.Pringle | Identify & manage team of volunteers | 2020-08-01 | 2020-08-01 | 0
|  |  | - Schedule regular maintenance sessions | 2020-09-01 | Ongoing
2020-11-01 | Playing Fields - Equipment to clean | C.Hodges | All equipment to be cleaned | 2021-04-01 | 2021-06-01 | 0
2021-05-01 | Public Footpath Sign at end of Avenue - clear branches/foliage | C.Hodges | Cut back in order to make sign visible | 2021-06-01 | 2021-06-01 | 0
2021-05-01 | Chevron Sign on Bend approaching Cedar Garth - repair | C. Hodges | Sign needs lifting & brackets tightening | 2021-06-01 | 2021-06-01 | 0
2021-05-01 | New Dog Bin - to be sited at end of alotments near telegraph pole | S.Lowe | New / additional bin as recommended by Dog Warden | 2021-06-01 | 2021-06-01 | 0
2021-05-01 | Institute Frontage needs weed clearing on car park area | C.Hodges | Weed needs clearing | 2021-06-01 | 2021-06-01 | 0